## IT onsite
# | Tasks | Detailed description | Proposed timeline | EF's responsible team/department | EF's input (what EF should to do to line up with the schedule) | VPB's Responsible team/department | VPBank's input (what VPB should to do to line up with the schedule) | Actual finished day | Delay time (if any) | Reason for delay (Each party must key in if there's any | Proposed solution
1. Hardware and software procurement
1 | For first version on 20th July | Hardware and software must be ready on 17 Jul because EF need 3 days for deployment | Now - 17 Jul | Quang, Phong | Confirm hardware/software suggestion from VPB - Help VPB to provide free software if necessary
1.1 | Hardware preparation: - 1 test server | Test server is all in one server (Database server, application server, web server) | Now - 17 Jul | Quang, Phong
1.2 | Software/middleware preparation: - OS: Redhat linux 5.7+ - Database: Oracle 11g Enterprise Edition - Web server: Tomcat 7.0.54, Nginx 1.7+ - Java: JDK 1.6+ (64bit) | - VPB buy necessary software (Redhat linux, Oracle) and prepare other free software - EF support VPB to provide free softwares with expected version: Tomcat, Nginx, JDK if VPB can not provide them - VPB install OS and other software/middleware in the test server | Now - 17 Jul | Quang, Phong | - Help VPB to provide free software if necessary
2 | For other versions from version 4th August | All production servers (3 servers) must be ready. This version need helping in network configuartion from VPB side, so EF need 5 days for deployment | 18 Jul - 28 Jul | Quang, Phong
2.1 | Hardware preparation: 3 production server - 1 Database server - 1 Application server - 1 Web server - SAN | From version 4th August, i-Factor system will be deployed in production servers, but the test server must be kept for update, test purpose after system is lanched | 18 Jul - 28 Jul | Quang, Phong | Confirm hardware/software suggestion from VP
2.2 | Software/middleware preparation - OS: Redhat linux 5.7+ - Database: Oracle 11g Enterprise Edition - Web server: Tomcat 7.0.54, Nginx 1.7+ - Java: JDK 1.6+ (64bit) | -VPB install OS and other software/middleware and production servers | 18 Jul - 28 Jul | Quang, Phong | - Help VPB to provide free software if necessary | [6 empty] | Completed
2.3 | Buy Domain name and SSL certificate | After marketing team confirm about product name, domain name | 12 Jul - 12 Aug
2. Network configuration
1 | Basic network configuartion | After production servers are ready, configure the servers so they can connect each others and connect to others systems of VPB (Email, SMS, Corebanking) | 29 Jul - 1 Aug | Quang, Phong, Zhang | Test, confirm that servers can connect
2 | Network configuration | - Domain and SSL configuration - Port debugging - Routing and network adjustment - Firewall setting adjustment | 4 Aug – 29 Aug (Parallel with SIT) | Quang, Phong, Zhang | Test, confirm that servers can connect | [6 empty] | On track
3. Interface preparation
1 | Build interface specification | EF and VPB define specification based on process of i-Factor system | Now - 21 Jul | Quang, Phong, Zhang | -EF provide first draff of interface specification - Discuss to finalize the interface specification
2 | Develop interface | VPB develop the interface, provide to EF then EF connect to VPB system via interface | 22 Jul - 31 Aug | Quang, Phong, Zhang | - Connect to VPB's interface, test and confirm the interface reach requirement
3 | Debug interface | Test, debut interface and fix errors if any | 1 Sep - 15 Sep | Quang, Phong, Zhang | - Provide personnel information - Connect to VPB's interface, test and confirm the interface work well
4. SIT (System Intergration Test)
1 | Provide personnel information and testing data | 1. Provide personnel for testing 2. Provide testing data (Adjust network configuration take place parallel with SIT) | 1 Aug – 4 Aug | Quang, Phong, Zhang, Kawa, ZhiChao | Provide personnel information of EF side | [6 empty] | Delayed
2 | Running SIT | Build test cases, provide test cases' result and feedback | 4 Aug – 29 Aug | All WS member | - Test system (separately with VPB team) - Fix errors if any
5. UAT (User Acceptance Test)
1 | Running UAT | At the same period of UAT, prepare a test environment for requirements validation after launching. Perform pilot run in production environment 2 weeks before system launch, and continue to run UAT in test environment in parallel | 1 Sep – 30 Sep | Quang, Phong, Zhang | Fixed errors if any
6. System official launching preparation
1 | Prepare for lauching | - Perform pilot run in production environment 2 weeks before system launch, and continue to run UAT in test environment in parallel | 16 Sep – 30 Sep | Quang, Phong, Zhang