## 工作表1
No | Date | Original Change | Requirment Change | Status | Next step | Improve
1 | 20th June | seller and buyer application data field without the data field of “the nearest branch for contract signing” | seller and buyer application data field update | Approval | Developed before 20th Juny
2 | 19th June | for signing a closed transaction VPBank wants to offer Seller and Buyer, 2 options: 1. Use e-Signature 2. Sign Sub-Contract in VPBank Branch | change in the auction process will create significant delays，offer seller and buyer a new opinion to sign contract | Reject | It will be developed after 20th Juny
3 | 19th June | Original email/SMS service | Addition of 4 email/SMS interface include: 1. The SME has completed their application; 2. The buyer has completed their application; 3. The SME has successfully uploaded their invoice; 4. The invoice is accepted to auction. | Approval | Developed before 20th Juny
4 | 19th June |  | In the SME admission stage, the system needs to tell if the SME belongs to the segment “SME” or “Micro SME”. This will affect the maximum invoice amount limit and maximum platform (revolving) limit of the SME. This part should already be done because before running the scorecards, the segment needs to be determined. | Approval | Developed before 20th Juny
5 | 19th June |  | Marking those invoices with deviation in the system. The following is the rules: i. Invoice amount - platform allows deviation of maximum 5% of the invoice amount limit. Therefore for micro SME, invoice amount between 0.8-0.84 is deviation. Bigger than 0.84 can never be accepted. ii. Invoice term - platform allows deviation from 35 days invoice term to 25 days invoice term.[Need calendar] Therefore, term between 25-35 is deviation. Less than 25 days can never be accepted. iii. The system needs to tell the person in the approval team if the invoice is within deviation. If he/she clicks “accept” button, the system should be able to tell that this is a case where deviation is accepted. iv. If the invoice term is in deviation, and the staff in the approval team accepts it, the system should assign a different cut-off date (22 days) for this invoice from other invoices. | Approval | Developed before 20th Juny | opinion 4 is rejected, IT development will provide a solution to discuss.
6 | 19th June |  | Original invoice verification: i. The staff in the underwriting team need to have the right to tick in a checkbox when the original invoice has been received. This checkbox can be ticked anytime once an invoice is uploaded to the system by the SME. This checkbox only affects the disbursement decision, but not whether the invoice will be approval or whether the auction will be closed if price is matched. ii. The system should support the function of searching by 1. unique invoice ID, 2. SME company name, 3. SME tax code, so that when the original invoice is sent to VPBank, the staff in the underwriting team can be able to find which invoice submission does it refer to. | Approval | Developed before 20th Juny
7 | 19th June |  | Suggest if there is any alternative way except running a report, to let VPBank to reassess the invoices before they expire, because the IT’s opinion is that there can be other better ways. | Agree | IT development team will provide a solution to discuss
8 | 19th June |  | During the invoice delivery process, the staff in the underwriting team and approval team can always be able to see the SME profile that has been created during SME admission process, because the two teams will compare the company profile information with the invoice details that are submitted for underwriting purpose. | Approval | Developed before 20th Juny
9 | 19th June |  | From system point of view, for the question of “Choose the most 5 main debtors in the eligible debtor list”, we could use the same searching method on market invoice. It’s difficult to use drop down list, becoz hundreds of companies are on the eligibility list. | Approval | Developed before 20th Juny
10 | 18th June |  | From system point of view, for the question of “Choose the most 5 main debtors in the eligible debtor list”, we could use the same searching method on market invoice. | Dicuss | Pls provide development team the eligible debtor list, if decide this function.
11 | 18th June | risk level: high,medium,low | risk level: high,low(include original high,low level)
12 | 18th June | risk field：invoice amount and risk level | risk field： invoice amount
13 | 18th June | none | point out the invoices with deviation
14 | 18th June | Original invoice will be send to VPB after signed contract | Original invoice will be send to VPB anytime after the invoice upload
15